## Slide 1: SW Alliances’ Rapid Diagnostic Pathway for Lung Cancer
Somerset, Wiltshire, Avon and Gloucester Cancer Alliance Transformation Project Update

## Slide 2: Project Milestone achievement
Deliverable / milestone | Salisbury NHS Foundation Trust | Royal United Hospitals Bath NHS Foundation Trust | University Hospitals Bristol NHS Foundation Trust | North Bristol NHS Trust | Taunton and Somerset NHS Foundation Trust | Yeovil District Hospital NHS Foundation Trust | Weston Area Healthcare Trust | Gloucestershire Hospitals NHS Foundation Trust
All patients will have access to a same day walk-in chest X-ray service |  |  |  |  |  |  |  | 
Adoption of SWRDPLC (not timescales) |  |  |  |  |  |  |  | ‘
Systems will allow patients with a negative diagnosis to leave the pathway without the need for an outpatient appointment |  |  |  |  |  |  |  | 
All GP Chest X-rays will be reported consistently, using the South West Chest X-ray Reporting Tool (or locally agreed alternative) |  |  |  |  |  |  |  | 
Collect information on chest X-ray codes and related activity and outcomes |  |  |  |  |  |  |  | 
X-ray and CT reporting backlogs will be cleared, facilitating a reduction in time between diagnostic activities and supporting either same day chest x-ray and CT |  |  |  |  |  |  |  | 
Radiographers will be trained to report X-rays either CXR or others so as to enable same day reporting of CXRs |  |  |  |  |  |  |  | 

## Slide 3: Risks
Deliverable / milestone | Salisbury NHS Foundation Trust | Royal United Hospitals Bath NHS Foundation Trust | University Hospitals Bristol NHS Foundation Trust | North Bristol NHS Trust | Taunton and Somerset NHS Foundation Trust | Yeovil District Hospital NHS Foundation Trust | Weston Area Healthcare Trust | Gloucestershire Hospitals NHS Foundation Trust
Risks (reported by providers) | Triage cost and loss of OPA income | Diagnostic sustainability CXR CT capacity | Incomplete data set | NRDP timescales re. CT access and reporting |  | Single respiratory physician Support required re D/C without OPA post normal CT | Retirement of CXR reporting Radiographer | Radiology capacity
Risks (reported by project team) | OPA capacity Internal escalation CT step required NRDP timescales | NRDP timescales | Incomplete data set | D/C post normal CT step required | NRDP timescales | Single point failure D/C post normal CT step required | Reporting capability to be confirmed | NRDP timescales

## Slide 4: Q1 2018/19 Timed pathway steps
Chart: 
| CDP | NRDP | NBT | GLOS | TST | YDH | SDH | PHNT
Wait between CXR perform to report | 7 | 1 | 3.3333 | 1 | 1 | 0 | 0.53333 | 4
Wait between CXR and CT | 7 | 3 | 9.8333 | 6.5 | 6.5 | 12.7667 | 8.0667 | 16.5
Wait for CT report | 7 | 3 | 1.3333 | 2 | 3 | 0 | 0.43333 | 1
Wait for OPA | 7 | 3 | 6.3333 | 6 | 7.7 | 14.9 | 13.3 | 4.25

## Slide 5: Q1 2018/19 Chest X-Ray report distribution
Chart: 
| GLOS | NBT | TST | YDH | SDH
CX3 | 16 | 14 | 10 | 8.3333 | 33.6667
Non CX3 | 1877 | 2100 | 1154 | 544 | 824
Total | 1893 | 2114 | 1164 | 552.3333 | 858
% CX3 | 0.0084522 | 0.0066225 | 0.0085911 | 0.015088 | 0.04
% Non CX3 | 0.99155 | 0.99338 | 0.99141 | 0.98491 | 0.96037

## Slide 6
Why CX reporting tool? (RUH)
Structured reporting template
Introduce consistent vocabulary between radiologists Reduce ambiguity
Enable consistently useful reports
Promote adherence to guidelines
Structured reporting in breast cancer used for some time - shown to assist education and practice consistency, and assisted in research & performance evaluation

## Slide 7
CX Reporting Tool (RUH)
Month | CX1 | CX2 | CX3* | No code**
April | 927 | 263 | 20 | 194
May | 748 | 266 | 26 | 212
June | 746 | 224 | 18 | 158
Jul | 685 | 194 | 18 | 127
Aug | 614 | 190 | 27 | 121

## Slide 8: Q1 2018/19 Non Cancers in CX3 cohort
Chart: 
| GLOS | TST | YDH | SDH | PHNT
Non Cancer | 0.1785 | 0.7 | 0.54833 | 0.82 | 0.77
Abnormal CT requires OPA | 0.8215 | 0.3 | 0.45167 | 0.18 | 0.23
Notes: Abnormal CT not = cancer due to local pathway variation re OPA use

## Slide 9: Diagnostic Breakdown post CT Q1 2018/19
Chart: 
| GLOS | NBT | UHB | RUH | TST | YDH | SDH | PHNT
SCLC | 0 | 0.0611 | 0.66667 | 0.03 | 0 | 0.047619 | 0 | 0.025
NSCLC | 0.3 | 0.28667 | 0.06 | 0.18 | 0.2 | 0.23095 | 0.19 | 0.135
Other respiratory disease | 0.05 | 0 | 0.073333 | 0.05 | 0.11 | 0.089286 | 0.33433 | 0.025
Notes: Link with low CX3 threshold with increased other respiratory disease

## Slide 10: RUH Pathology audit

## Slide 11: Steering group recommendations
CX3 code utilisation
CX3 standardisation required
Best practice pathway recommendation requires patient experience information
Triage tariff equity with virtual clinic tariff
RUH patient information – good practice
To consider further:
Navigator / pathway coordinator post requirement
Best practice patient information leaflet

## Slide 13: Next Steps
CX3 standardisation
Full data reporting
Patient experience survey
GP CXR clarity survey
Route to Diagnosis audit
Clinical Leadership
NSF pathway activity fund proposals
Q2 2018/19 Evaluation report
Clinical Advisory Forum 12.2.18
Notes: Patient experience work – collecting provider plans and encourage all to undertake
Route to diagnosis - £3000 per provider as part of pathway activity fund allocations
Clinical leadership – EOI circulated
NSF pathway activity fund proposals – deadlines missed +++ opportunity to put in via STP funds to be spent and changes implemented by April 2019

## Slide 14: National Support Funding
NHS England has allocated National Support Funding (NSF) to the Somerset, Wiltshire, Avon & Gloucestershire (SWAG) Cancer Alliance
The criteria for the use of this money is:
Meeting the 62 day standard and sustaining it;
100% implementation of the rapid prostate, colorectal and lung pathways in 100% trusts across the Alliance geography by March 2019 (clinical order not timings);
100% implementation of clinical protocols and a system for remote monitoring to support stratification of breast cancer patients across the Alliance geography by March 2019.
Quarters 1&2 2018/19 | £750k
Quarters 3&4 2018/19 | £950k
Total 2018/19 | £1700k

## Slide 15: Indicative Lung Pathway Activity Fund – bids via STP’s
STP Indicative Allocation |  |  | 
STP | NSF | CTF 18/19 | Total
BNSSG | 53K | 68K | 121K
BSW | 31K | 35K | 66K
Glos | 47K | 33K | 80K
Somerset | 37K | 27K | 64K

## Slide 16: Pathway Activity Fund Proposals
Pathway Milestone
Direct access to urgent or routine CXR from primary care – arrangement should be in place for hot reporting (or within 24 hours), action on abnormal result is secondary care responsibility.
Escalation from CXR to CT (same day/within 72 hours) – ‘straight-to-CT’ arrangement in place as described in NOLCP implementation guide.
Direct access to CT (same day/ within 72 hours) – Arrangements can be put in place with primary care for patients with normal CXR but when clinical symptoms and risk factors continue to cause concern. Timeframes should be the same as for those with abnormal CT.
Triage by radiologist or lung physician – local protocol developed to facilitate streamlined triage process. If lung cancer can be ruled out there is no need to see patient in a cancer clinic. Local arrangements to be made with primary care over redirection to respiratory clinic or refer back to primary care.
Direct biopsy option – for when initial triage suggests cancer but patient unlikely to be suitable for curative treatment, consider developing local protocol.
Fast track lung cancer clinic - meet lung cancer nurse specialist (diagnostic process plan, diagnostic planning meeting prior to clinic, treatment of co-morbidity and palliation/ treatment of symptoms).
Curative Intent Management pathway - test bundle requested at first outpatient appointment including at least PET-CT spirometry, with lung function and cardiac assessment/ ECHO as required. Consider local arrangement / networking to reduce PET-CT delays at this stage.
MDT and discussion of treatment options (It is envisaged that when the new guidance on multidisciplinary team meetings is published in summer 2018, there will be a recommendation that some patients on clear and agreed cancer pathways may be discussed more briefly either at the beginning, or end, of the MDT).
Follow up in Lung Cancer Clinic: cancer confirmed and treatment options discussed, or if no cancer diagnosis then manage/discharge (this should be at earliest opportunity e.g. by day 1-6 stage if CT excludes cancer). Any further investigations following MDT will have been completed by day 28.
Notes: To implement further steps towards full compliance with National Rapid Diagnostic Pathway funds need to be spent and sustainable change needs to be implemented by April 2019 to qualify for fund

## Slide 17: Pathway Activity Fund Proposals to Date
CA Route to diagnosis audit £3,000 / provider £21,000
NBT £10,000 for 136 CT reports / upskill backfill
£4,000 ICE referral for DA CT (non CX3’s)
£20,000 admin support of Lung CNS (patient contact no cancer diagnosis (MECC opportunity) or cancer diagnosis and early diagnostic planning)
UHB £17,000 Curative intent management pathway
        clinical review, audit and protocol development
BNSSG - £34,830 15 weeks of additional outpatient follow up calculated until the end of the financial year.
Notes: Upskill backfill is radiologists to report CXR and CT

## Slide 18: Pathway Activity Fund Proposals P&ED funding allocation includes
Wiltshire LA / CCG lung health work with ‘turning point’
Notes: ? Upskilling staff for sign and symptom recognition and signposting or a form of lung health check with referral pathway for high risk DA CT