## Slide 1: Teledermatology Pilot – B&NES, Wilts and Somerset CCGs at RUH Andy Jennings, Senior Commissioning Manager, Wilts CCG / BSW STP

## Slide 2: RUH catchment

## Slide 3: Practices
Volunteers …. Near/far, large/small
B&NES x 4 (different 4 for each different model)
Wilts x 4 (same 4 throughout)
(Somerset x 2)

## Slide 4: Process (1)
“Based on Leeds model” THANK YOU!
All potential 2ww
Ipod, dermatoscope (Schuco DermLite DL200 Hybrid), connection kit, Consultant Connect, eRS
One set of kit per ~6,000 on list
Minimum three images (area, close-up, dermatoscope)
Consultant Connect to receive/transfer images to Practice system and eRS referral
Add images to 2ww referral
Send via eRS

## Slide 5: Process (2)
RUH receive and review from eRS
Book those truly 2ww
Respond to GP for those not 2ww – for GP management
Downgrade those needing to be seen by consultant as routine/urgent but not 2ww
Responses copied to patient

## Slide 6: Outcomes

## Slide 7: Issues (1)
A lot of Consultant time wasted, carrying out supporting admin process, e.g. to save across images from eRS onto hospital PAS system
Double data-entry
Increased risk of error due to clunkiness between eRS and PAS
Scope for confusion for GPs and patients – 2ww booking created, but then cancelled/amended
At pilot stage, no job-planned time allocated – essential for wider roll-out

## Slide 8: Issues (2)
Image quality – resolution/orientation/pressure/etc
No images / poor images = remains 2ww
Need to implement templated response letters

## Slide 9: Timescale
Initial discussions – Dec 2018
Go-live - Apr 19
Review points – Aug 19, Oct 19
Revision to different model – Nov 19
Future review points - monthly
Planned end date – Mar 20
Wider roll-out – Apr 20 onwards (subject to timelines for job planning changes)

## Slide 10: Next Steps
Revised pilot model process about to be introduced:
  All potential 2ww send via Consultant Connect
  As Advice & Guidance
  Response to GP within 2 working days (aiming for same day) –
    Refer, or guidance for management in primary care
    Priority, to refer
  GP then raise as 2ww or routine or urgent
  RUH confident of being able to see all subsequent 2ww in [14 days minus the time spent on the A&G process]
  direct listing to ENT/OMFS
  becomes part of OP block funding arrangements
From Apr 2020: (1) wider roll-out (2) 28 Day FDS

## Slide 11: Any Questions?