## Slide 1: One stop myeloma diagnosis pathway at the RUH: Presentation of initial audit and patient feedback.
Dr Angie Habgood (Haematology SpR) & Dr Sarah Mitchard (Haematology SHO)
Dr Jo Crowe (Haematology Consultant)

## Slide 2: RUH myeloma standard clinic pathway
Referral
6 steps from referral to treatment/active monitoring
Each step in the pathway has a waiting time
* Depending on clinical urgency, MDT may happen in conjunction with clinic and commencement of treatment
Triage
Clinic
BMAT
+/- PET CT
MDT*
Clinic
Treatment/
Active monitoring
+/- PET CT

## Slide 3: RUH myeloma one stop pathway
Referral
Triage
Clinic, PET CT and BMAT on same day
MDT*
Clinic
Treatment/Active monitoring
4 steps from referral to treatment/active monitoring
All investigations take place on the day of first clinic assessment
* Depending on clinical urgency, MDT may happen in conjunction with clinic and commencement of treatment

## Slide 4: Patient appointment letter
Copies available to view

## Slide 5: Audit of data: Standard vs one stop pathway
Data collection from standard and ‘one stop’ pathway with a focus on :
Time from triage to bone marrow aspirate and trephine (BMAT) procedure
Time from triage to PET CT scan
Time from triage to patient receiving diagnosis
Time from triage to day one of treatment/active monitoring if applicable (i.e. multiple myeloma confirmed)
We also took the opportunity to look at other data for future improvement work eg:
Time from BMAT to report authorised
To check whether important cytogenetic information from the BMAT was sufficient to risk stratify patients and guide prognosis and treatment
Are we achieving our aims?

## Slide 6: Analysis of pathway time points:
Standard 2WW Pathway (results in days) |  |  |  |  | 
 | Average | Median |  |  | 
Triage to clinic | 10.1 | 6.0 |  |  | 
Triage to BMAT | 36.1 | 23.0 |  |  | 
Time from BMAT to report | 12.1 | 12.0 |  |  | 
Triage to PET-CT | 43.1 | 32.0 |  |  | 
Triage to diagnosis | 64.2 | 61.0 |  |  | 
Referral to treatment/active monitoring | 76.5 | 68.5 |  |  | 
One Stop Pathway (results in days) |  |  |  |  |  |  | 
 | Average | Median | Median |  |  |  | 
Triage to clinic | 10.6 | 12.5 | 12.5 |  |  |  | 
Triage to BMAT | 11.6 | 13.5 | 13.5 |  |  |  | 
Time from BMAT to report | 18.6 | 17 | 17 |  |  |  | 
Triage to PET-CT | 10.8 | 11 | 11 |  |  |  | 
Triage to diagnosis | 34.6 |  | 36.0 |  |  |  | 
Referral to treatment /active monitoring | 38 | 48 | 48 |  |  |  | 

## Slide 7
Myeloma one stop clinic significantly reduced the time from triage to BMAT and PET CT*
Chart: Triage to BMAT
| Standard pathway | One stop pathway
 | 36 | 11.6
Chart: Triage to PET CT
| Standard pathway | One stop pathway
 | 43 | 10.8
*Two patients in One Stop pathway did not have PET-CT (therefore mean values not identical)

## Slide 8
Myeloma one stop clinic reduced the time from triage to patients being told their diagnosis.
Chart: Triage to diagnosis
| Standard pathway | One stop pathway
Series 1 | 64.2 | 34.6

## Slide 9
Myeloma one stop clinic therefore reduced the overall time from referral to treatment/active monitoring
Chart: Referral to treatment
| Standard pathway | One stop pathway
 | 76.5 | 38

## Slide 10
There are delays from BMAT procedure to authorised report* in both pathways
Chart: Time from BMAT to report
| Standard pathway | One stop pathway
 | 12 | 18.6
*Trephine biopsies are not reported at RUH (outsourced)

## Slide 11: Patient experience: Patient feedback questionnaire
We worked with our Patient Experience team to try to get feedback from patients on their treatment pathway.
Questionnaire for patients attending clinic during June – Aug 2025
Targeted those who were included in audit (identified via hospital number)
Included standard and one-stop pathway patients
Asked about their experience of appointments and diagnosis
Also took the opportunity to get feedback on other cancer survey measures
Total of 28 questionnaires distributed
Are we achieving our aims?

## Slide 12: Patient feedback questionnaire
Copies of full questionnaire available to view

## Slide 13: Patient feedback questionnaire
Summary of patient feedback questionnaire |  |  |  |  | 
Number of questionnaires distributed | 28 |  | Number of standard pathway responses | 8 | 
Number returned | 12 |  | Number of one stop pathway responses | 4 | 
Response rate | 43% |  |  |  | 
Patients identified from original data set
Any patient who had F2F appointment in June/Jul/Aug 2025
Given out by reception staff
Anonymous (tear off front sheet – no patient identifiers)
No clinician involvement
Limitations:
Reasonable response rate but still small number of replies
Those who were part of standard pathway had their diagnosis many months previously (patients were in different stages of their myeloma monitoring/treatment)

## Slide 14: Patients were generally reassured by the timing of their appointments
Chart: Standard pathway - how do you feel about multiple appointments on different days?
| Overwhelmed | Reassured
Series 1 | 2 | 6
Chart: One stop pathway - how do you feel about multiple appointments on the same day?
| Overwhelmed | Reassured
 | 0 | 4

## Slide 15: Patients would generally prefer to have all appointments on one day
Chart: 
| No preference | Spread over days | All on same day
Number of patients | 3 | 1 | 8

## Slide 16: We also asked whether they had all the information they needed about their tests and appointments:
Standard pathway
One-stop pathway
Chart: 
| Yes | No
Number | 6 | 2
Chart: 
| Yes | No
Number | 3 | 1

## Slide 17: And whether they met one of our CNS nurses:
Standard pathway
Chart: 
| yes | no | no but contact details given
number | 6 | 1 | 1
One-stop pathway
Chart: 
| yes
number | 4

## Slide 18: Key findings and plans for further improvement
The main aims of the one stop myeloma pathway are being met:
Significantly reduces time from triage to BMAT and PET CT
Reduces time from triage to day one of treatment/active monitoring
Patients are generally reassured to have all appointments in one day and most would prefer this
There are still improvements to make with our service overall (both pathways):
Triaging – plan to introduce new SOP and make use of iStopMM tool
Reporting times on bone marrow trephines
Cytogenetic information
Communication and information to patients
Could we improve 2WW referral pathway by having additional BMAT on same day (without the PET-CT)?